## Development Plan
ID | Module | Task | Spec ref | Owner | Priority | Start | End | Weeks | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
T01 | Planning | Analyze instructor requirements; confirm scope without gamification | Sec. I–II | Hiếu | Must | 1 | 1 | 1 | Done
T02 | Planning | Write functional specification | Sec. I–IX | Hiếu | Must | 1 | 1 | 1 | Done
T03 | Design | UI design – User version (Figma) | Sec. VII | Hải | Must | 1 | 2 | 2 | Done
T04 | Design | UI design – Admin version (Figma) | Sec. VII | Hải | Must | 1 | 2 | 2 | Done
T05 | Database | ERD and schema design | Sec. V | Thiện | Must | 1 | 2 | 2 | Done
T06 | Setup | Repos, environments, project structure, Git workflow | NFR-06 | Thiện | Must | 1 | 2 | 2 | In progress
T07 | Database | Migrations and seed data (roles, admin, sample users and posts) | Sec. V | Thiện | Must | 2 | 3 | 2 | In progress
T08 | Back-end | API conventions, validation, error handling, Swagger/Postman | Sec. VI | Thiện | Must | 2 | 3 | 2 | In progress
T09 | Front-end | App scaffold: routing, layout, shared components, API client | Sec. 7.3 | Hải | Must | 2 | 3 | 2 | In progress
T10 | Auth | Register, login, logout API with JWT and role guard | FR-AUTH-01–05 | Thiện | Must | 2 | 3 | 2 | In progress
T11 | Auth | Register and login screens, protected routes | FR-AUTH-01–04 | Hải | Must | 3 | 3 | 1 | Not started
T12 | Profile | Profile API: view, edit info, avatar and cover upload | FR-PROF-01–03 | Thiện | Must | 3 | 4 | 2 | Not started
T13 | Profile | Profile page and edit form; people search | FR-PROF-01–05 | Hải | Must | 4 | 4 | 1 | Not started
T14 | Posts | Post API and image upload (create, view, delete) | FR-POST-01,04,05 | Hiếu | Must | 3 | 4 | 2 | In progress
T15 | Posts | Post composer and post card UI | FR-POST-01,04,05 | Hiếu | Must | 3 | 4 | 2 | In progress
T16 | Posts | Video upload and edit post | FR-POST-02,03 | Hiếu | Should | 5 | 5 | 1 | Not started
T17 | Newsfeed | Newsfeed API with pagination | FR-FEED-01,02 | Hiếu | Must | 4 | 5 | 2 | In progress
T18 | Newsfeed | Newsfeed UI: infinite scroll, empty state | FR-FEED-01–04 | Hiếu | Must | 4 | 5 | 2 | Not started
T19 | Interaction | Like API and heart toggle UI | FR-INT-01,02 | Hải | Must | 4 | 5 | 2 | Not started
T20 | Interaction | Comment API and UI (add, list, delete) | FR-INT-03,04 | Hải | Must | 4 | 5 | 2 | Not started
T21 | Friends | Friend API: request, accept, decline, cancel, unfriend, lists | FR-FRND-01–05 | Hiếu | Must | 5 | 6 | 2 | Not started
T22 | Friends | Friend UI: requests, friend list, search, profile buttons | FR-FRND-01–05 | Hiếu | Must | 5 | 6 | 2 | Not started
T23 | Messaging | Messaging API with Socket.IO: send, receive, history | FR-MSG-01–03 | Thiện | Must | 5 | 6 | 2 | Not started
T24 | Messaging | Chat UI: conversation list, window, unread badge | FR-MSG-01–04 | Hải | Must | 5 | 6 | 2 | Not started
T25 | Status | Status API and UI: update, clear, display, online dot | FR-STAT-01–04 | Hải | Must | 6 | 6 | 1 | Not started
T26 | Admin | Admin API: manage users and posts, delete | FR-ADM-02,03,05,06 | Thiện | Must | 6 | 7 | 2 | Not started
T27 | Admin | Statistics API: users and posts | FR-ADM-01,07,08 | Thiện | Must | 6 | 7 | 2 | Not started
T28 | Admin | Admin UI: dashboard, charts, management tables | FR-ADM-01–08 | Hải | Must | 7 | 7 | 1 | Not started
T29 | Extras | Could items: notifications, replies, suggestions, visibility | Could items | Hiếu | Could | 7 | 8 | 2 | Not started
T30 | QA | API tests and security review (permissions, XSS, uploads) | NFR-02, BR-01–08 | Thiện | Must | 7 | 7 | 1 | Not started
T31 | QA | Integration and UI testing, responsive check, bug fixing | NFR-01, 03, 04 | Hiếu | Must | 7 | 8 | 2 | Not started
T32 | Deploy | Deploy app and database; load demo data | NFR-05 | Thiện | Must | 8 | 8 | 1 | Not started
T33 | Delivery | Report, API docs and user guide | NFR-06 | Hải | Must | 8 | 8 | 1 | Not started
T34 | Delivery | Demo rehearsal and submission | All | Hiếu | Must | 8 | 8 | 1 | Not started